## Sheet1
Work Breakdown Structure
No | Name | Status | Assignee | Start date | End date | Note
1 | Preparation
1.1 | Determine domain business
1.2 | Create a plan for implementation
1.3 | Determine targeted users
1.4 | Choosing technologies
2 | Gathering requirement
3 | Analysis requirement
4 | System design
4.1 | Design use cases diagram
4.2 | Design overview architecture
5 | Implementation
5.1 | Setup repository
5.2 | Setup deployment server
5.3 | Setup development environment
5.4 | Implement Authentication Provider with IS4
5.4.1 | Create project structure
5.4.2 | Add Identity Server
5.4.3 | Config client
5.4.4 | Seeding data
5.5 | Implement RESAPI with DDD for Admin
5.5.1 | Create project structure
5.5.2 | Login with Identity
5.5.3 | Add swagger
5.5.4 | Implement Domain entity
5.5.5 | Connect to MongoDB
5.5.6 | Add API Versioning
5.5.7 | Implement CQRS in Application
5.5.8 | Create REST API
5.6 | Implement Admin UI
5.6.1 | Create project structure
5.6.2 | Integrate with Backend API
5.6.3 | Login with Identity
5.6.4 | Manage questions
5.6.5 | Manage exam
5.6.6 | Manage result
5.6.7 | Manage user
5.7 | Implement API for Portal
5.7.1 | Create project structure
5.7.2 | Athorize with Identity
5.7.3 | REST API
5.8 | Implement Quiz Portal
5.8.1 | Create project structure
5.8.2 | Integrate with Backend API
5.8.3 | Login with Identity
5.8.4 | List exam
5.8.5 | View exam detail
5.8.6 | Take exam
5.8.7 | View result
5.8.8 | Profile
5.8.9 | View history
6 | Testing
7 | Deployment